## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Gather ANPR + ATCC datasets from Kaggle / existing sources and validate structure | MUST HAVE | Kaggle account | Ananya Garg | Completed
S1 | S1 | US-002 | Perform dataset preprocessing – resize images, clean labels, remove corrupt images | MUST HAVE | Jupyter/Colab | Ananya Garg | Completed
S1 | S1 | US-003 | Perform initial exploratory analysis to understand dataset, class distribution, etc. | SHOULD HAVE | Python libraries | Ananya Garg | Completed
S1 | S1 | US-004 | Convert dataset into YOLO format (train/val/test splits, labels formatting) | MUST HAVE | YOLO knowledge | Ananya Garg | Completed
S2 | S2 | US-005 | Train YOLO model for ANPR (license plate detection) | MUST HAVE | Ultralytics YOLO | Ananya Garg | Completed
S2 | S2 | US-006 | Train YOLO model for ATCC (vehicle detection, classification) | MUST HAVE | Ultralytics YOLO | Ananya Garg | Completed
S2 | S2 | US-007 | Perform evaluation – precision, recall, mAP for both models | MUST HAVE | training outputs | Ananya Garg | Completed
S2 | S2 | US-008 | Perform hyperparameter tuning for improved accuracy | COULD HAVE | resources | Ananya Garg | Completed
S3 | S3 | US-009 | Integrate OCR (Tesseract / EasyOCR) to extract license plate text from YOLO crops | MUST HAVE | OCR libraries | Ananya Garg | Completed
S3 | S3 | US-010 | Build real-time ANPR pipeline: detect → crop → OCR → display | MUST HAVE | YOLO + OCR | Ananya Garg | Completed
S3 | S3 | US-011 | Build real-time ATCC pipeline: detect → count vehicles → classify types | MUST HAVE | YOLO model | Ananya Garg | Completed
S4 | S4 | US-012 | Create Streamlit dashboard for displaying ANPR + ATCC results | MUST HAVE | Streamlit | Ananya Garg | Completed
S4 | S4 | US-013 | Integrate both ANPR and ATCC in a single unified dashboard | MUST HAVE | YOLO + Streamlit | Ananya Garg | Completed
S4 | S4 | US-014 | Add real-time webcam/video input support | SHOULD HAVE | OpenCV | Ananya Garg | Completed
S4 | S4 | US-015 | Prepare final deliverables, documentation, and presentation | MUST HAVE | Project files | Ananya Garg | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Dataset not fully organized | Created structured folder layout
Sprint 1 | Day 2 | Missing annotations for some number plates | Manually corrected and completed annotations
Sprint 2 | Day 3 | Model overfitting during training | Added data augmentation
Sprint 2 | Day 5 | Accuracy drop in validation | Tuned hyperparameters and learning rate
Sprint 3 | Day 2 | ANPR detection slow | Optimized frame extraction and batch size
Sprint 4 | Day 4 | ATCC counting mismatch | Fixed bounding box tracking logic
Sprint 5 | Day 3 | UI layout inconsistency | Redesigned UI with fixed component structure

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint | Start Date | End Date | Ananya | Start documenting each preprocessing step clearly | Stop re-checking same dataset files repeatedly | Continue consistent daily updates | Created a structured dataset documentation and naming convention
2 | Sprint 1 | 2025-10-25 | 2025-10-31 | Ananya | Start testing YOLO model with smaller batches | Stop training on full dataset without validation | Continue model performance monitoring | Implemented validation split and batch-wise training
3 | Sprint 2 | 2025-11-01 | 2025-11-07 | Ananya | Start integrating ANPR pipeline with ATCC module | Stop delaying integration until full completion | Continue tracking accuracy metrics | Combined ANPR detection output with traffic counting pipeline
4 | Sprint 3 | 2025-11-08 | 2025-11-14 | Ananya | Start writing API endpoints early | Stop manual testing repeatedly | Continue structured development | Developed FastAPI endpoints for ANPR + ATCC
5 | Sprint 4 | 2025-11-15 | 2025-11-21 | Ananya | Start UI wireframing | Stop making UI changes without proper layout | Continue iterative testing | Designed dashboards for Smart Traffic Management
6 | Sprint 5 | 2025-11-22 | 2025-11-28 | Ananya | Start optimizing model inference speed | Stop testing on CPU only | Continue maintaining logs | Shifted to GPU-based inference and optimized detection speed
7 | Sprint 6 | 2025-11-29 | 2025-12-05 | Ananya | Start preparing final documentation early | Stop last-minute combining of modules | Continue code cleanup | Created final technical report + project demonstration