## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Ananya Garg | 2025-11-05 | YOLO model failing to detect plates in low-light videos | S1 | Ananya Garg | Model Accuracy | Improved preprocessing + brightness normalization | 2025-11-07 | Closed | Resolved with preprocessing
2 | Ananya Garg | 2025-11-06 | OCR misreads similar characters (0/O, 5/S) | S1 | Ananya Garg | OCR Error | Applied character-level post-processing rules | 2025-11-08 | Closed | Accuracy improved
3 | Ananya Garg | 2025-11-07 | ATCC classifier misclassifies trucks as buses | S2 | Ananya Garg | Classification Error | Added more training samples for trucks | 2025-11-09 | Closed | Balanced dataset
4 | Ananya Garg | 2025-11-08 | Streamlit UI slow when loading video frames | S2 | Ananya Garg | Performance | Optimized frame reading and caching | 2025-11-10 | Closed | Working smoothly
5 | Ananya Garg | 2025-11-09 | OCR returns blank output for angled plates | S3 | Ananya Garg | OCR Error | Added perspective correction | 2025-11-11 | Closed | Improved OCR
6 | Ananya Garg | 2025-11-10 | Dashboard not updating vehicle counts in real-time | S4 | Ananya Garg | UI Bug | Fixed state refresh method | 2025-11-12 | Closed | Now updating
7 | Ananya Garg | 2025-11-11 | Integrated model produces delayed response (>2 sec) | S4 | Ananya Garg | Performance | Optimized inference pipeline | 2025-11-13 | Closed | Latency reduced
8 | Ananya Garg | 2025-11-12 | Some plate numbers not logged in CSV | S4 | Ananya Garg | Logging Issue | Corrected file write operation | 2025-11-14 | Closed | Logging consistent
9 | Ananya Garg | 2025-11-13 | Final UI deployment failing on PythonAnywhere | S4 | Ananya Garg | Deployment Issue | Adjusted WSGI + runtime settings | 2025-11-15 | Closed | Deployment successful

## Sheet2
Logical
User Interface
Maintainability
Standards
Others